## strep
NO. | INCOMING DATE | REF. LOGISTIC / PPC | CUSTOMER A/C TYPE / REG | WBS | PART NAME | PART NUMBER | SERIAL NUMBER | COMPONENT ORDER | MDR / DOC / DEFECT | CAPABILITY | IWO NO. | AREA / FO | IWO DATE | WORKSHEET NO. | REMARK MWS | TEST RESULT (ADA/TIDAK) | SCHEDULE (DELIVERY ON TIME) | ECD FINISH (WORKDAYS) | SELISIH (WORK DAYS) | PROSENTASE SCHEDULE | * WORKSHEET DATE | * WORKSHEET APPROVAL DATE | SELISIH WORKSHEET DATE | FORM OUT NO. | TANDA TERIMA FO NO. | TANDA TERIMA FO DATE | * STRIPPING REPORT DATE | * STRIPPING ORDER BY SAP DATE | * PROSENTASE BDP | QTY BDP | SELISIH ORDER (WORK DAYS) | TIME STRIPPING (WORK DAYS) | MAX STRIPPING DATE | SELISIH STRIPPING (WORK DAYS) | %TASE STRIPPING | STATUS [S / (U/S)] | FINISH DATE2 | MEN POWERS | MEN HOURS | DOCUMENT PENYERTA | SHIP./TRANSFER (TT) DATE | SHIP./TRANSFER (TT) NO. | ISR NO. | SELISIH SHIPPING (WORK DAYS) | %TASE | REMARK | S | U/S | RAI | SAL | FO | PP | WEEK | STATUS | YEAR | S. PROGRESS
358 | 2024-07-17 | 048/BA-STB/LG3600/07/2024 | ROKAF | 4/S95-19010008-01-04-83 | BOX ASSY RELAY | 35-66665-0023 | 35-N-072 | Repair |  | NK | 2407-00358 | FO |  | - |  |  |  |  | FALSE |  |  |  |  | 014/24 | 098/TFO/09/24 | 2024-09-18 | [9 empty] | RAI |  |  |  |  | 2024-09-13 | 089/TT/09/24 | [6 empty] | 1 |  | 1 |  | Week-36 | Form Out [014/24], 098/TFO/09/24 | 2024
958 | 2023-11-01 | 096/BA-STB/LG3600/10/2023 | THAI | 4/S90-23028064-01-02-32 | DIFF CTL SELTR VALVE | CA91300-0001 | 2111 | Repair |  | K | 2311-00958 | HY |  | EHM-R061 |  |  | 2024-01-24 | 60 | -36 | 100% | 0 | 0 | -1 |  |  |  | 2023-11-07 | 2023-11-07 | 0% | 4 | 0 | 20 | 2023-11-29 | -16 | 100% | U/S | 2023-12-05 |  |  | RR, WS, LABEL | 2023-12-06 | 198/TT/12/23 | ISR-019/23 | 1 | 100% |  |  | 1 |  |  |  | 100% | Week-49 | Finished [U/S], 198/TT/12/23 | 2023
325 | 2023-03-06 | 020/BA-STB/LG5300/03/2023 | DIR. PRODUKSI | Y/R@S | FUEL FLOW METER INDICATOR | AC410045 / 9-464-40 | H4798 | IRAN |  | K | 2303-00325 | IN | 2023-03-06 | IN-065 |  |  | 2023-05-29 | 60 |  | - | 2023-03-06 | 2023-03-06 | 0 |  |  |  | 2023-03-20 | 2023-03-20 | 0% | 2 | 0 | 20 | 2023-04-03 | -10 | 100% | RAI |  |  |  |  | 2023-08-16 | 130/TT/08/23 |  | - |  |  |  |  | 1 |  |  | 100% | Week-33 | Finished [RAI], 130/TT/08/23 | 2023
339 | 2023-03-09 | 022/BA-STB/LG5300/03/2023 | ROKAF | 4/S95-19010008-01-03-78 | INVERTER | SPC60K | 194 | Repair |  | NK | 2303-00339 | EL | 2023-03-09 | TD-EL-42 |  |  | 2023-06-01 | 60 |  | - | 2023-03-09 | 2023-03-09 | 0 |  |  |  | - | - |  |  |  | 20 | 2023-04-06 |  |  | RAI |  |  |  |  | 2023-05-23 | 087/TT/05/23 |  | - |  |  |  |  | 1 |  |  | 100% | Week-21 | Finished [RAI], 087/TT/05/23 | 2023
941 | 2023-10-27 | 094/BA-STB/LG3600/10/2023 | TUDM | 4/S95-19010127-01-08-92 | EMERGENCY POWER SUPPLY | 501-1228-06 | 9253 | Repair |  | K | 2310-00941 | EL |  | EL-010 |  |  | 2024-01-19 | 60 | 241 | 19.93% | 0 | 0 | -1 |  |  |  | 2023-11-06 | 2023-11-06 | 100% | 2 | 0 | 20 | 2023-11-24 | -14 | 100% | S | 2024-12-23 |  |  | RR, ARC, WS, LABEL | 2024-12-31 | 069/TT/12/24 |  | 6 | 100% |  | 1 |  |  |  |  | 100% | Week-52 | Finished [S], 069/TT/12/24 | 2024
951 | 2023-10-27 | 094/BA-STB/LG3600/10/2023 | TUDM | 4/S95-19010127-01-08-78 | BRAKE ASSEMBLY | AHA1802 | VH010 | Repair |  | K | 2310-00951 | AP |  | ACC-P011 |  |  | 2024-01-19 | 60 |  | - | 0 | 0 | -1 |  |  |  | 2023-11-17 | 2023-11-17 | 71.43% | 7 | 0 | 20 | 2023-11-24 | -5 | 100% | [8 empty] | - | [5 empty] | 1 |  | 60% |  |  |  | ON PROCESS

## control
CUSTOMER | IWO NO. | INCOMING | SCHEDULE | FINISH DATE | STATUS | PART NAME | PART NUMBER | SERI NO. | JOC NO. | SHOP | C/O | %TASE | BDP NAME | BDP NUMBER | BDP NUMBER Eqv. | QTY | UNIT | OP NUMBER | OP DATE | DEFECT | MT NUMBER | MT QTY | MT DATE | REMARK | REMARK DATE | KODE STATUS | ECD BULAN
ROKAF | 2407-00358 | 2024-07-17 |  | 2024-09-13 | Form Out [014/24], 098/TFO/09/24 | BOX ASSY RELAY | 35-66665-0023 | 35-N-072 | 4/S95-19010008-01-04-83 | FO | Repair
THAI | 2311-00958 | 2023-11-01 | 2024-01-24 | 2023-12-06 | Finished [U/S], 198/TT/12/23 | DIFF CTL SELTR VALVE | CA91300-0001 | 2111 | 4/S90-23028064-01-02-32 | HY | Repair | 0% | PACKING, SELECTOR VALVE | A632-60701 |  | 2 | EA | 20649286 | 2023-11-07
[13 empty] | PACKING, SELECTOR VALVE | SD8-4 |  | 2 | EA | 20649286 | 2023-11-07
[13 empty] | PACKING, SELECTOR VALVE | JSD18-7 |  | 2 | EA | 20649286 | 2023-11-07
[13 empty] | RETAINER | 23351AC050LE |  | 1 | EA | 20649286 | 2023-11-07
DIR. PRODUKSI | 2303-00325 | 2023-03-06 | 2023-05-29 | 2023-08-16 | Finished [RAI], 130/TT/08/23 | FUEL FLOW METER INDICATOR | AC410045 / 9-464-40 | H4798 | Y/R@S | IN | IRAN | 0% | CONNECTOR, STRIP | CP22-05 |  | 2 | EA | 20633345 | 2023-03-20
[13 empty] | DISPLAY, LCD | DP07-02 |  | 1 | EA | 20633345 | 2023-03-20
ROKAF | 2303-00339 | 2023-03-09 | 2023-06-01 | 2023-05-23 | Finished [RAI], 087/TT/05/23 | INVERTER | SPC60K | 194 | 4/S95-19010008-01-03-78 | EL | Repair
TUDM | 2310-00941 | 2023-10-27 | 2024-01-19 | 2024-12-31 | Finished [S], 069/TT/12/24 | EMERGENCY POWER SUPPLY | 501-1228-06 | 9253 | 4/S95-19010127-01-08-92 | EL | Repair | 100% | BATTERY CELL | 549-1170-01 | AQS4016 | 12 | EA | 20649235 | 2023-11-06 | Low Voltage | 4902228430 | 12 | 2024-12-03
[13 empty] | STRAP | MS3368-3-9C | MS3367-7-9 | 12 | EA | 20649235 | 2023-11-06 | One Time Used | 4902211860 | 12 | 2024-08-29
TUDM | 2310-00951 | 2023-10-27 | 2024-01-19 | 0 | ON PROCESS | BRAKE ASSEMBLY | AHA1802 | VH010 | 4/S95-19010127-01-08-78 | AP | Repair | 71.43% | O-RING | DAS2118-12 |  | 10 | EA | 20650078 | 2023-11-17 | One Time Used | 4902228834 | 10 | 2024-12-05
[13 empty] | O-RING | DAS2137-23 | MS28775-218 | 5 | EA | 20650078 | 2023-11-17 | One Time Used | 4902221565 | 5 | 2024-11-06
[13 empty] | O-RING | DSR4331-1128 |  | 5 | EA | 20650078 | 2023-11-17 | One Time Used | 4902228834 | 5 | 2024-12-05
[13 empty] | PLATE | AHO88704 |  | 1 | EA | 20650078 | 2023-11-17 | Decolourision
[13 empty] | PLATE | AHO89759 |  | 1 | EA | 20650078 | 2023-11-17 | Decolourision
[13 empty] | RING BACK-UP | DSR4332-1218 |  | 5 | EA | 20650078 | 2023-11-17 | One Time Used | 4902228834 | 5 | 2024-12-05
[13 empty] | RING SEALING | DAS2119-4 |  | 2 | EA | 20650078 | 2023-11-17 | One Time Used | 4902228834 | 2 | 2024-12-05